## Product Backlog
PRODUCT BACKLOG
ID | AS A … | I WANT TO … | SO THAT … | PRIORITY | SPRINT | STATUS | STATUS | PRIORITY
1 | Investor | have Project Proposal | I can understand the ideas, designs and architecture of project. | High | 0 | Not Started | Not Started | High
2 | Developer | have Scenario | I can understand real-life business processes. | High | 0 | Not Started | In Progress | Medium
3 | Developer | have Domain Model | I can understand real-life business processes and connect them to software (write source code). | High | 0 | Not Started | Complete | Low
4 | Developer | have Projduct Backlog | I can know the features that need to be completed, the products that need to be completed, and to plan and estimate the implementation costs. | High | 0 | Not Started | Overdue
5 | Developer | have Prototype | I can understand the business process flows and corresponding interfaces. | High | 0 | Not Started | On Hold
6 | Developer | have Architecture | I can know the system architecture from different perspectives, the technologies and tools chosen to build the system. | High | 0 | Not Started
7 | Developer | have Proof of Concept | I can know if I am capable of doing difficult features. | High | 0 | Not Started
8 | Developer | have Project Plan | I can know the time, cost of each stage and important stage of the project. | High | 0 | Not Started
9 | Developer | have Coding Standards | I can comply with the project's common source code standards. | High | 0 | Not Started
10 | Investor | have Documentation for installing and configuring the automatic build system | I can save time later and know how to maintain/upgrade the system. | High
11 | Investor | have Documentation for installing tools for system testing | I can save time and know how to test the system later, as well as be able to evaluate the system based on the test results. | High | 0 | Not Started
12 | Investor | have Documentation for installing the environment and compiling the system | I can save time and know how to maintain/upgrade the system later. | High | 0 | Not Started
13 | Investor | have System implementation guide | users can use their system to generate revenue and profit. | High | 0 | Not Started
14 | End User | have Product installation and usage instructions | I can know how to use the product for better experience. | High | 0 | Not Started
15 | End User | sign up by Email | I can have an account. | High | 0 | Not Started
16 | End User | sign up by Phone number | I can have an account. | High
17 | End User | sign in | I can use app feartures. | High
18 | End User | view list of exercises | I can choose the suitable exercise. | Medium
19 | End User | watch a exercise | I can workout base on it. | High
20 | End User | search for excercises | I can find the suitable excercise. | Medium
21 | End User | view list of gyms | I can choose the suitable gym. | Low
22 | End User | search for gyms | I can go to the suitable gym. | Low
23 | End User | track my workouts | I know how effective the workouts. | High
24 | End User | weight control | I need a recommended food ration | High
25 | End User | take survey | I know my health conditions and have advices and recommends. | High
26 | End User | set goals | I know if I am doing well. | Medium
27 | End User | search for foods | I know healthy foods and use them. | Low
28 | End User | give feedbacks | App can be improve. | Low
29 | Brand | increase revenue | I need to regist service facility. | Medium
30 | Brand | attract customers | I want to apply discount, offer to my service facility. | Medium
31 | Super Administrator | create Administrator account | App have human resources to participate in system management. | High
32 | Administrator | app have variety of exercises | I can add exercises. | High
33 | Administrator | review the registrations of brands | app need to display registrations. | High
34 | Administrator | app have variety of food data | I can add food data. | High
35
36